## Month
Senior Honors Thesis Timline | [10 empty] | Project Schedule
© 2014-2019 Vertex42 LLC
|  | Start Date | 2021-08-24 | [8 empty] | Project Schedule Template
Month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | Edit the Start date in cell E3
| 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | Notes
| 2021-08-31 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01
Phase | 2021-08-31: Enrolled in thesis hours |  | RELATED TEMPLATES
One | 2021-08-31: Submitted prospectus, Scheduled weekly meetings with Dr.Shah. | How many sources I should have | ► Gantt Chart Template
| 2021-09-01: Review past thesis, meet my librerian. |  | ► Project Management Templates
| 2021-09-01: Literature review. |  | ► Business Templates
Phase | 2021-10-01: Meet Thesis Director, 2nd Reader, and Honors.
Two | 2021-10-01: Draft an appropriate number of pages on your background readings
Work toward developing your thesis statement
Register for the December 4th Winter Reset
| 2021-11-01: Submit drafts as needed before thanksgiving | Friday, November 20th
Speak with your academic advisor to have them enroll you in the second thesis course
Phase | 2021-12-01: My Thesis Director should assign a IP grade
Three | 2021-12-01: Ensure that I am enrolled in 4399 | thesis liasion
Make sure I see the 4399
Attend the OURMA Thesis Binding
My first full draft should be complete
Schedule your final thesis defense
Send your final thesis document to all three members
Defend your Senior thesis
Make sure all required documents have been received OURMA
S